## Test Plan
Test Plan
1) Test Plan ID: | Techlandbd-WebApp-001
2) Introduction: | It is System Test Plan for Online Shop. The purpose of this test plan to find out the system bugs and ensure that this system is working by according to its requirements.
3)Test Items: | User Interface.
4) References: | Requirements, Projects Plan, Test Strategy, High level Design doc, Low Level Design doc, Process guide line doc, Prototypes.
5) Features to be Tested: | User Interface:
1) Register page,
2) Login page.
6)Features not to be Tested: | NA
7) Entry Criteria: | A) Test Design: Team formation, Responsibilities, Schedule, Requirements, Test Case Template etc...
B) Test Execution: Readiness of Test Lab Readiness of AUT Requirements Test Case Docs Test Data Defect Report Template Etc.…
8) Exit Criteria: | All Possible test cases executed
9) Suspension Criteria: | NA
10) Roles & Responsibilities: | Mamun Bhuiyan
Tester, Test Case Documentation, Test execution, Defect reporting and tracking.
11) Schedule: | Task:
1) Creating Test Plan- 4/15/24 to 4/17/24
2) Test Case Creation- 4/17/24 to 4/21/24
3)Test Case Execution- 4/21/24 to 4/24/24
12) Training: | NA
13) Risk & Mitigation: | NA
14) Test Environment: | Windows 10/11 – Chrome, Firefox and Edge
15)Test Deliverables: | Test Plan, Mind Maps, Review Reports, RTM Test Scenario, Test Case, Test Summary Report, Bug Report.
16) Approvals: | NA
17) Glossary: | AUT- Application Under Test, PIN- Project Initiation Note, SRS- Software Requirements Specification.

## Test Scenario
Project Name
Reference Document
Created By | Mamun Bhuiyan
Creation Date | 2024-04-17
Approval Date | 2024-04-25
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the URL in different browsers. | P0 | 1
TS_002 |  | Validate the "Register Account" functionality | P1 | 44
TS_003 |  | Validate the working of the "Login" functionality. | P0 | 26

## TestCase
Product Name |  | techlandbd | TC Start Date | 2024-04-17 | TC Execution Start Date | 2024-04-21 |  |  |  |  | TEST CASE
Module Name |  | Sign Up and Sign In | TC End Date | 4/21/2024 | TC Execution End Date | 2024-04-24 |  |  |  |  | PASS | 44
Epic |  |  | Test Case Developed By | Mamun Bhuiyan | Browser (tested) | [5 empty] | FAIL | 27
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | [5 empty] | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 71
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome, Mozilla Firefox, Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'techlandbd' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Sign Up | Checking Sign Up page screen will appear after clicking on Sign Up link or Sign Up botton. | Should be appear | Found as per expectation | NA |  |  |  | Passed
3 |  |  |  | Checking all Sign Up related elements and fields are present on the Sign Up page. | Should be as per requirement | Found as per expectation | NA |  |  |  | Passed
4 |  |  |  | Checking spelling and grammatical mistakes. | No mistakes | Found as per expectation | NA |  |  |  | Passed
5 |  |  |  | Checking all the allignments of displayed elements and fields of Sign Up screen. | No allignment mistake | Found as per expectation | NA |  |  |  | Passed
6 |  |  |  | Checking the size, colour and font of displayed elements and fields. | Should be correct and match UI elements specification | Not found as per expectation | NA |  |  |  | Failed
7 |  |  |  | Checking the hover is appear on Sign Up/Register button after pointing on it. | Hover should appear | Found as per expectation | NA |  |  |  | Passed
8 |  |  |  | Checking mendatory field is marked with a red asterisk | Should marked with red asterisk | Found as per expectation | NA |  |  |  | Passed
9 |  |  |  | Checking the allignment of Sign Up button and it's colour, font size and button size. | Should be accurate | Not found as per expectation | NA |  |  |  | Failed
10 |  |  |  | Checking the field size | Should not be too much width | Not found as per expectation | NA |  |  |  | Failed
11 |  | Usability Testing |  | Checking Keyboard Enter button is working perfectly or not. | Should be | Found as per expectation | Pressed enter button in every field |  |  |  | Passed
12 |  |  |  | Checking Keyboard Tab button is working perfectly or not. | Should be | Found as per expectation | Pressed tab button in every field |  |  |  | Passed
13 |  |  |  | Checking up down arrow button is working or not. | Should be | Not found as per expectation | Pressed updown button in every field |  |  |  | Passed
14 |  |  |  | Checking left, right arrow is working or not. | Should be | Found as per expectation | Pressed left-right button in every field |  |  |  | Failed
15 |  |  |  | Checking copy paste is working in every field. | Should be | Found as per expectation | 1234copypaste |  |  |  | Passed
16 |  | Compatibility Testing |  | Checking the website is run properly on every OS. | Should run | Found as per expectation | linux, mac, Windows |  |  |  | Passed
17 |  |  |  | Checking the webapp is run properly on every Bowser. | Should run | Found as per expectation | Chrome,Bing,Bravo,Edge |  |  |  | Passed
18 |  |  |  | Checking the Content of webapp is loading perfectly. | Should be | Found as per expectation | Chrome,Bing,Bravo,Edge |  |  |  | Passed
19 |  | Responsiveness Testing |  | Checking the webapp is Responsiveness or not. | Should be Responsive | Found as per expectation | linux, mac, Windows, Android, Apple devices |  |  |  | Passed
20 |  |  |  | Checking the Display View on every OS. | Should be Same | Found as per expectation | linux, mac, Windows, Android, Apple devices |  |  |  | Passed
21 |  | Functionality Testing |  | Keeping the all madatory fields are kept blank. | Should be | Found as per expectation | NA |  |  |  | Passed
22 |  |  |  | Checking the name field is case sensative | Should not | Found as per expectation | james bond |  |  |  | Passed
23 |  |  |  | Checking the first position of name field by entering space | Should not accept | Not found as per expectation | james bond |  |  |  | Failed
24 |  |  |  | Checking the name field is by entering the characters without letters | Should not accept | Not found as per expectation | 321321$%^% |  |  |  | Failed
25 |  |  |  | Checking the name field by keeping blank | Should get warning message | Found as per expectation | NA |  |  |  | Passed
26 |  |  |  | Checking the name field by adding only one character | Should not accept | Not found as per expectation | $ |  |  |  | Failed
27 |  |  |  | Checking the name field by entering Special characters between first and last letter of the name. | Should get a warning message and not be accepted. | Not found as per expectation | jam@#,.es |  |  |  | Failed
28 |  |  |  | Checking the name field by entering Special characters at the first and last position of the name. | Should get a warning message and not be accepted. | Not found as per expectation | <>$#james$#$. |  |  |  | Failed
29 |  |  |  | Checking the name field by entering Space between first and last position of the name. | Should get a warning message and not be accepted. | Not found as per expectation | jam es |  |  |  | Failed
30 |  |  |  | Checking the name field by entering Space at the first and last position of the name. | Should get a warning message and not be accepted. | Not found as per expectation | james |  |  |  | Failed
31 |  |  |  | Checking contact number field by entering space at the first position. | Should get a warning message and not be accepted. | Found as per expectation | 1628198305 |  |  |  | Passed
32 |  |  |  | Checking contact number field by entering other numerical characters except 01 at the first & second position. | Should get a warning message and not be accepted. | Not found as per expectation | 12628198305 |  |  |  | Failed
33 |  |  |  | Checking contact number field by entering other characters except numbers. | Should get a warning message and not be accepted. | Found as per expectation | njksdfla%$$., |  |  |  | Passed
34 |  |  |  | Checking the contact number field must be taking 11 digit of numeric characters. | Should be | Not found as per expectation | 162819 |  |  |  | Failed
35 |  |  |  | Checking that user is not allowed to get register with the same used number for registration. | Should not get allowed | Not found as per expectation | 1628198303 |  |  |  | Failed
36 |  |  |  | Checking that valid email addresses are acceptable. | Should accept | Found as per expectation | goodboymamun000@gmail.com |  |  |  | Failed
37 |  |  |  | Checking that email field is not accepting spaces at first position. | Should not accept | Found as per expectation | goodboymamun000@gmail.com |  |  |  | Passed
38 |  |  |  | Checking that invalid email addresses are not acceptable. | Should not accept | Not found as per expectation | goodboymamun000@mail.com |  |  |  | Failed
39 |  |  |  | Checking that email verification link was send to the user email address successfully. | Should be send | Not found as per expectation | goodboymamun000@gmail.com |  |  |  | Failed
40 |  |  |  | Checking that useer was getting warning meesage after enter blank input. | Should be | Found as per expectation | NA |  |  |  | Passed
41 |  |  |  | Checking that password field is taking input | Should be | Found as per expectation | 1234 |  |  |  | Passed
42 |  |  |  | Checking that password field is taking input minimum 8 to 16 characters. | Should be | Not found as per expectation | 1234 |  |  |  | Failed
43 |  |  |  | Checking that password field is must contain special characters, at least one uppercase character and have a numerical number. | Should have | Not found as per expectation | 1234 |  |  |  | Failed
44 |  |  |  | Checking that password field has eye icon for view password. | Should have | Not found as per expectation | NA |  |  |  | Failed
45 |  |  |  | Checking that password data is masked. | Should be | Found as per expectation | 1234 |  |  |  | Passed
|  |  | Improvement Scope | Can add first name and last name.
Can add capctha
Can add an eye icon on the password field
46 |  | UI Testing | Sign In | Checking that login page will appear after clicking on a login link or login button. | Shoukd be | Found as per expectation | NA |  |  |  | Passed
47 |  |  |  | Checking that all required elements and fields are presented on the login page. | Shoukd be | Found as per expectation | NA |  |  |  | Passed
48 |  |  |  | Checking spelling and gramatical mistakes. | Should not have | Found as per expectation | NA |  |  |  | Passed
49 |  |  |  | Checking the allignments of all the presented elements. | Perfect allignments | Found as per expectation | NA |  |  |  | Passed
50 |  |  |  | Checking the size, colour and ui of different elements. | Should match the specifications | Not found as per expectation | NA |  |  |  | Failed
51 |  |  |  | Checking login page title | Should have | Not found as per expectation | NA |  |  |  | Failed
52 |  |  |  | Checking mendatory field is marked with a red asterisk | Should be | Not found as per expectation | NA |  |  |  | Failed
53 |  |  |  | Checking that password field has an eye icon | Should have | Not found as per expectation | NA |  |  |  | Failed
54 |  | Usability Testing |  | Checking Keyboard Enter button is working perfectly or not. | Should be | Found as per expectation | Pressed enter button in every field |  |  |  | Passed
55 |  |  |  | Checking Keyboard Tab button is working perfectly or not. | Should be | Found as per expectation | Pressed tab button in every field |  |  |  | Passed
56 |  |  |  | Checking up down arrow button is working or not. | Should be | Found as per expectation | Pressed updown button in every field |  |  |  | Passed
57 |  |  |  | Checking left, right arrow is working or not. | Should be | Found as per expectation | Pressed left-right button in every field |  |  |  | Passed
58 |  |  |  | Checking copy paste is working in every field. | Should be | Found as per expectation | 1234copypaste |  |  |  | Passed
59 |  | Compatibility Testing |  | Checking the website is run properly on every OS. | Should run | Found as per expectation | linux, mac, Windows |  |  |  | Passed
60 |  |  |  | Checking the webapp is run properly on every Bowser. | Should run | Found as per expectation | Chrome,Bing,Bravo,Edge |  |  |  | Passed
61 |  |  |  | Checking the Content of webapp is loading perfectly. | Should be | Found as per expectation | Chrome,Bing,Bravo,Edge |  |  |  | Passed
62 |  | Responsiveness Testing |  | Checking the webapp is Responsiveness or not. | Should be Responsive | Found as per expectation | linux, mac, Windows, Android, Apple devices |  |  |  | Passed
63 |  |  |  | Checking the Display View on every OS. | Should be Same | Found as per expectation | linux, mac, Windows, Android, Apple devices |  |  |  | Passed
64 |  | Functionality Testing |  | Checking the login functionality by keepping all mandatory fields blank. | Should get a warning message to fill up the form. | Found as per expectation | NA |  |  |  | Passed
65 |  |  |  | Checking that the valid credentials are acceptable to get logged in. | Should be | Found as per expectation | goodboymamun000@gmail.com,1234 |  |  |  | Passed
66 |  |  |  | Checking that the invalid credentials are not acceptable to get logged in. | Should not | Found as per expectation | goodboymamun000@gl.com, 0125$%## |  |  |  | Passed
67 |  |  |  | Checking that the user are not allowed to logged in without password. | Should not | Found as per expectation | NA |  |  |  | Passed
68 |  |  |  | Checking the forgot password functionality. | Shoud send an email for recovering account. | Not found as per expectation | goodboymamun000@gmail.com |  |  |  | Failed
69 |  |  |  | Checking that old password for reset password. | Should get a warning message and asking for set new password. | Not found as per expectation | 1234 |  |  |  | Failed
70 |  |  |  | Checking the login functionality with newly chhanged password. | Should get logged in | Found as per expectation | 1234 |  |  |  | Passed
71 |  |  |  | Checking reset the password link is sent to valid email address. | Should send to the valid mail address | Not found as per expectation | goodboymamun000@gmail.com |  |  |  | Failed
|  |  | Improvement Scope | Can add remember me checkbox
Can add page title

## Test Summary Report
Test Case Report
Project Name | techlandbd
Module Name | Sign Up and Sign In |  |  |  |  | Total No. | Status | Result :
Test Case Version | [5 empty] | 44 | PASS
Written By | Mamun Bhuiyan |  |  |  |  | 27 | FAIL
Executed By | Mamun Bhuiyan |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope |  | 0 | 0 | 0
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 44 | 27 | 0 | 0 | 71
Grand Total | 44 | 27 | 0 | 0 | 71
Received
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.
Test Case Report
GENERAL INFORMATION
Test Stage: | Functionality
Test date: | 2024-04-17 | System Date, if applicable: | N/A
Tester: | Mamun Bhuiyan | Test Case Number: | # SL 01
Test Case Description: | User should not register to the system without entering valid credientials and password including at least one uppercase one numeric and minimum length should be eight.
Results: | Fail | Incident Number, if applicable | N/A
INTRODUCTION
Requirement(s) to be tested: | User should enter valid credientials and password including at least one uppercase one numeric and minimum length should be eight.
Rules and Responsibilities: | N/A
Set Up Procedures: | 1. Ensure that your device has Internet access
2. Open Google Chrome
Stop Procedures: | 1. Screenshot of that error.
2. Record test result.
ENVIRONMENTAL NEEDS
Hardware: | N/A
Software: | Google Chrome
Procedural Requirements: | N/A
TEST
Test Items and Features: | Password field for user registrations. Requirements source not applicable.
Input Specification: | 1. Email: goodboymamun000@gmail.com
2. Valid Captcha
Procedural Steps: | 1. Go to : https://www.techlandbd.com/
2. Clicked on Sign Up button
4. Enter Invalid mail and credentials
5. Enter Password
6. Clicked on Sign Up button
Expected Result of the Case: | User should not registered with Entering Invalid credentials.
ACTUAL RESULTS
Output Specification: | 1. User can registered with invalid password.

## Bug Report
Bug Reporting
# SL 01
Issue: Registered with invalid email address
Reproducing Steps:
1. Goto the URL:
https://www.techlandbd.com/
2. Click on Register button.
3. Fill up all the fields with invalid email address.
4. Now, Click on Register button.
Env: Production
Module: Sign Up
Severity: P1
Screenshot: Invalid email address error
Responsible QA: Mamun Bhuiyan
Bug Reporting
# SL 02
Issue: Registered with invalid name
Reproducing Steps:
1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with invalid credentials 4.Click 'Create an Account'
https://www.techlandbd.com/
2. Click on Register button.
3. Fill up all the fields with invalid name.
4. Now, Click on Register button.
Env: Production
Module: Sign Up
Severity: P1
Screenshot: Invalid name
Responsible QA: Mamun Bhuiyan
Bug Reporting
# SL 03
Issue: Registered with invalid mobile number
Reproducing Steps:
1. Goto the URL
https://www.techlandbd.com/
2. Click on Register button.
3. Fill up all the fields with invalid Mobile number.
4. Now, Click on Register button.
Env: Production
Module: Sign Up
Severity: P1
Screenshot: Invalid mobile number
Responsible QA: Mamun Bhuiyan
Bug Reporting
# SL 00
Issue:
Reproducing Steps:
1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with invalid credentials 4.Click 'Create an Account'
Env: Production
Module: Sign In
Severity: P1
no
Responsible QA: Mamun Bhuiyan
Bug Reporting
# SL 00
Issue:
Reproducing Steps:
1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with invalid credentials 4.Click 'Create an Account'
Env: Production
Module: Sign In
Severity: P1
no
Responsible QA: Mamun Bhuiyan

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (71/71)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/71)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (44/71)*100 = 61.97
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (27/71)*100 = 38.03
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/71)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A